## Gantt Chart Template
Event Announcer |  |  | E
Task name | Start date | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 19.06.2025 | 2025-06-20
UI Wireframes & Prototyping | 2025-05-27 | bar: 2025-05-27 to 2025-05-30
MongoDB Schema & API Planning | 30.05.2025 | bar: 2025-05-31 to 2025-06-02
User Authentication Backend | 03.05.2025 | bar: 2025-06-03 to 2025-06-07
Dashboard club | 08.05.2025 | bar: 2025-06-08 to 2025-06-11
Event Registration Flow Backend | 13.06.2025 | bar: 2025-06-12 to 2025-06-13
Event CRUD API | 14.06.2025 | bar: 2025-06-14 to 2025-06-15
Build Event List UI (Frontend) | 16.05.2025 | bar: 2025-06-16
Admin Dashboard UI | 17.05.2025 | bar: 2025-06-17
Nakshatra Module UI + Backend | 18.05.2025 | bar: 2025-06-18
Integration + Axios Connection | 19.05.2025
Testing (Unit + Manual) | 19.05.2025
Deployment & Final Demo | 20.06.2025

## Assignees and Status
Assignees | Status
Andrew | Open
Helen | In process
Paul | Closed
Victoria | Done
Alex